## ReadMe
Kalasu Home Appliances Private Limited: readiness scorecard and remediation tracker
Diligence Readiness, Dissent Advisory. Fictional company; every figure is constructed for teaching. ₹ Cr unless a row says otherwise.
How to use
1 | Work alongside the course. Each worked example names the sheet it draws on.
2 | Change a blue input or a yellow choice and everything downstream recalculates: the score and heatmap, the request load, the routes, the critical path and the report.
3 | Compare the results with 09_Answer_Check. It flags any figure that differs from the course by more than its tolerance.
4 | Example: set 04_Triage C4 to 2 weeks and three fixes become disclosures, as Chapter III's quiz asks.
Colour legend
Blue text | Typed inputs from the case.
Black text | Formulas.
Green text | Links to another sheet.
Yellow fill | Choices the course invites you to change.
Sheets
01_Checklist | The 60 sweep items with severity, status and the evidence that proves each
02_Request_Load | The request list by workstream against the people who answer it
03_Heatmap | Readiness by workstream and severity, and the score
04_Triage | Each finding: exposure, cost and time to fix, and the route
05_Remediation | Actions with owners, dependencies, durations and evidence of closure
06_Critical_Path | Earliest finish against 4 January 2027 and the slack
07_Report | The one-page readiness report
08_AI_Spec | The specification for an AI tool
09_Answer_Check | Your figures against the course
The case
Product | Small kitchen appliances, GST at 18%
GMV the founders quote, FY26 | ₹49.12 Cr
Net revenue, FY26 | ₹30.00 Cr: website 40%, marketplaces 45%, quick commerce 15%
Contribution after marketing (CM3) | ₹3.39 Cr (11.3%)
EBITDA, FY26 | Loss of ₹4.53 Cr
Series A, April 2025 | ₹40.00 Cr from a domestic Category II AIF
Cash and investments, 31 March 2026 | ₹32.59 Cr
Framework and tax | Accounting Standards; Section 115BAA, now Section 200, 25.168%
Headcount | 50, all in Bengaluru

## 01_Checklist
The self-diligence sweep, 13 November 2026
Sixty items as the buyer's request list will test them. Weight is the severity: high 3, medium 2, low 1.
Score an unknown as a gap |  | No
Readiness score |  | 79.13%
ID | Workstream | Item | Severity | Status | Evidence | Weight | Credit | Issue
R-01 | Corporate and secretarial | Memorandum and articles current, with the Series A amendments filed | 3 | clean | MCA master data; MGT-14 SRNs | 3 | 1
R-02 | Corporate and secretarial | Register of members and share certificates agree with the cap table | 3 | clean | Register of members; cap table | 3 | 1
R-03 | Corporate and secretarial | Series A private placement: offer letter, separate bank account, allotment resolution | 3 | clean | PAS-4, PAS-5, bank statement, board minutes | 3 | 1
R-04 | Corporate and secretarial | Series A return of allotment filed within 15 days of allotment | 3 | gap | PAS-3 SRN and filing date | 3 | 0 | I-11
R-05 | Corporate and secretarial | ESOP scheme approved by special resolution before any grant | 3 | gap | MGT-14 for the resolution; grant letters | 3 | 0 | I-10
R-06 | Corporate and secretarial | Board minutes signed and entered within 30 days of each meeting | 2 | clean | Minute book | 2 | 1
R-07 | Corporate and secretarial | Every director’s disclosure of interest (MBP-1) taken at the first meeting of each year | 2 | clean | MBP-1 forms; board minutes | 2 | 1
R-08 | Corporate and secretarial | Related party transactions approved under Section 188 and consented to under the SHA | 3 | gap | Board resolution; investor consent | 3 | 0 | I-04
R-09 | Corporate and secretarial | Charge index on the MCA portal agrees with the lenders; satisfied charges closed | 2 | clean | MCA index of charges; bank letters | 2 | 1
R-10 | Corporate and secretarial | AOC-4 and MGT-7A for FY25 and FY26 filed on time | 2 | clean | SRNs and filing dates | 2 | 1
R-11 | Corporate and secretarial | DIR-3 KYC for every director and the DPT-3 return filed | 1 | clean | SRNs | 1 | 1
R-12 | Corporate and secretarial | Register of contracts with related parties (MBP-4) kept up to date | 2 | unknown | MBP-4 register | 2 | 0.5
R-13 | Financial reporting | FY25 and FY26 audited with unmodified opinions | 3 | clean | Audit reports | 3 | 1
R-14 | Financial reporting | CARO 2020 reports no undeposited statutory dues | 2 | clean | CARO paragraph 3(vii) | 2 | 1
R-15 | Financial reporting | CARO 2020 reports on the Series A allotment’s compliance | 2 | clean | CARO paragraph 3(x)(b) | 2 | 1
R-16 | Financial reporting | Audit trail enabled all year, with the auditor’s statement under Rule 11(g) | 2 | clean | Auditor’s report; software settings | 2 | 1
R-17 | Financial reporting | FY26 trial balance ties to the audited financial statements | 3 | clean | Trial balance; mapping | 3 | 1
R-18 | Financial reporting | FY27 monthly MIS ties to the books | 2 | clean | MIS; trial balance by month | 2 | 1
R-19 | Financial reporting | Gratuity measured under AS 15 on an actuarial valuation | 2 | gap | Actuarial report | 2 | 0 | I-08
R-20 | Financial reporting | Inventory aged and tested for net realisable value each quarter | 2 | unknown | Ageing report; NRV working | 2 | 0.5
R-21 | Financial reporting | Related party note under AS 18 lists every relative of a director | 2 | clean | FY26 notes to accounts | 2 | 1
R-22 | Financial reporting | Contingent liabilities note agrees with the notices received | 2 | clean | Notices register; FY26 notes | 2 | 1
R-23 | GST | Both GSTINs current, with every warehouse and fulfilment centre declared | 2 | clean | Registration certificates | 2 | 1
R-24 | GST | GSTR-1 and 3B filed on time every month on both GSTINs | 3 | clean | GST portal filing history | 3 | 1
R-25 | GST | GSTR-9 and 9C filed for FY25 | 2 | clean | Portal acknowledgements | 2 | 1
R-26 | GST | E-invoices generated for every business-to-business supply | 2 | clean | IRP reports | 2 | 1
R-27 | GST | Input tax credit claimed within GSTR-2B, with Rule 37A reversals tracked | 2 | unknown | ITC register against 2B | 2 | 0.5
R-28 | GST | Credit notes issued within the Section 34 time limit | 2 | unknown | Credit note register | 2 | 0.5
R-29 | GST | Section 52 TCS reconciled to the operators’ GSTR-8 and accepted on the portal | 1 | unknown | TCS credit statement | 1 | 0.5
R-30 | GST | No notices, demands or proceedings open on the portal | 3 | clean | Portal notices tab | 3 | 1
R-31 | GST | E-way bills for every stock transfer to Bhiwandi | 1 | clean | E-way bill register | 1 | 1
R-32 | Income tax and TDS | Returns and tax audit reports filed for tax years 2024-25 and 2025-26 | 3 | clean | ITR acknowledgements; Form 3CD | 3 | 1
R-33 | Income tax and TDS | Form 26AS and the AIS reviewed against the books | 2 | unknown | 26AS; AIS; ledger 1505 | 2 | 0.5
R-34 | Income tax and TDS | TDS returns filed every quarter with no defaults on TRACES | 3 | clean | TRACES justification reports | 3 | 1
R-35 | Income tax and TDS | TDS deducted under the section the service falls in | 2 | unknown | TDS register by vendor | 2 | 0.5
R-36 | Income tax and TDS | Micro and small enterprise dues paid within 45 days (Section 43B(h)) | 3 | gap | Payables ageing; MSME Form I; Form 3CD | 3 | 0 | I-03
R-37 | Income tax and TDS | No demands or proceedings open on the e-filing portal | 3 | clean | E-filing portal | 3 | 1
R-38 | Income tax and TDS | Advance tax position for loss years documented | 1 | clean | Computation of income | 1 | 1
R-39 | Income tax and TDS | Payments to relatives of directors at fair value (Section 40A(2)(b)) | 2 | unknown | Market rent study | 2 | 0.5
R-40 | Income tax and TDS | No international or specified domestic transactions needing a transfer pricing report | 1 | clean | Form 3CD | 1 | 1
R-41 | Payroll and labour | PF registration current and every monthly return filed by the 15th | 3 | clean | ECR challans | 3 | 1
R-42 | Payroll and labour | PF wages include allowances paid to every employee | 3 | gap | Salary register against ECR | 3 | 0 | I-07
R-43 | Payroll and labour | ESI contributions for every covered employee | 2 | clean | ESI challans | 2 | 1
R-44 | Payroll and labour | Professional tax registration and monthly returns in Karnataka | 1 | clean | PT returns | 1 | 1
R-45 | Payroll and labour | Gratuity nominations held for every employee | 1 | clean | Nomination forms | 1 | 1
R-46 | Payroll and labour | Internal Committee constituted and the POSH annual report filed | 2 | unknown | IC order; annual report | 2 | 0.5
R-47 | Payroll and labour | Employment contracts with confidentiality and invention assignment for every employee | 2 | clean | Contract files | 2 | 1
R-48 | Payroll and labour | Shops and Establishments registration current in Karnataka | 1 | clean | Registration certificate | 1 | 1
R-49 | Payroll and labour | Payroll applies the ₹25,000 PF wage ceiling notified on 17 September 2026 | 2 | clean | October 2026 ECR | 2 | 1
R-50 | Commercial | Marketplace and quick commerce agreements signed and current | 3 | clean | Seller agreements | 3 | 1
R-51 | Commercial | Contract manufacturing agreements cover quality, mould ownership and payment terms | 3 | clean | Manufacturing agreements | 3 | 1
R-52 | Commercial | Warehouse leases stamped and registered | 2 | clean | Lease deeds | 2 | 1
R-53 | Commercial | Warranty and returns policies on the website match the provisions in the accounts | 1 | clean | Website terms; provision working | 1 | 1
R-54 | Commercial | Change-of-control and assignment clauses listed for every material contract | 2 | unknown | Contract abstract | 2 | 0.5
R-55 | Commercial | Litigation and disputes register shows none open | 2 | clean | Disputes register; settlement agreement | 2 | 1
R-56 | Technology, IP and data | Trademark applications for the brand in the classes its products fall in | 3 | clean | IP India records | 3 | 1
R-57 | Technology, IP and data | Website terms and privacy notice current | 2 | clean | Website | 2 | 1
R-58 | Technology, IP and data | A plan for the DPDP Act duties that apply from May 2027 | 1 | clean | DPDP readiness plan | 1 | 1
R-59 | Technology, IP and data | Software licences and subscriptions held in the company’s name | 1 | clean | Licence register | 1 | 1
R-60 | Technology, IP and data | Domain names registered to the company, not to a founder | 1 | clean | Registrar records | 1 | 1

## 02_Request_Load
The request list against the people who answer it
The lead's first list by workstream, what the August data room already holds, and the hours each owner can give.
Count what the data room already holds |  | Yes
Weeks from appointment to the room opening |  | 10
Workstream | Requests | In the room | Open | Owner | Hours each | Hours
Corporate and secretarial | 34 | 22 | 12 | Company secretary | 1.5 | 18
Financial reporting | 40 | 18 | 22 | Finance lead | 3 | 66
GST | 22 | 6 | 16 | Tax consultant | 2.5 | 40
Income tax and TDS | 24 | 8 | 16 | Tax consultant | 2.5 | 40
Payroll and labour | 20 | 6 | 14 | HR and payroll | 2 | 28
Commercial | 26 | 14 | 12 | Founders’ office | 1.5 | 18
Technology, IP and data | 14 | 8 | 6 | CTO | 1 | 6
Owner | Open requests | Hours | Hours a week | Weeks
Company secretary | 12 | 18 | 6 | 3
Finance lead | 22 | 66 | 20 | 3.3
Tax consultant | 32 | 80 | 8 | 10
HR and payroll | 14 | 28 | 6 | 4.6667
Founders’ office | 12 | 18 | 6 | 3
CTO | 6 | 6 | 4 | 1.5
Requests on the list |  | 180
Open after the data room |  | 98
Weeks to a complete first pass |  | 10
Slowest owner |  | Tax consultant
Weeks to spare before the room opens |  | 0

## 03_Heatmap
Readiness by workstream and severity
Share of each cell's weight with its evidence in hand. Blank where a cell has no items.
Severity weight | 3 | 2 | 1
Workstream | High | Medium | Low | All
Corporate and secretarial | 50% | 90% | 100% | 65.52%
Financial reporting | 100% | 81.25% |  | 86.36%
GST | 100% | 80% | 75% | 86.11%
Income tax and TDS | 75% | 50% | 100% | 70%
Payroll and labour | 50% | 87.5% | 100% | 76.47%
Commercial | 100% | 83.33% | 100% | 92.31%
Technology, IP and data | 100% | 100% | 100% | 100%
Readiness score at the sweep |  | 79.13%
Gaps |  | 6
Unknown items |  | 10
Clean |  | 44
Readiness score, unknowns as gaps |  | 71.65%
Lowest cell |  | 50%

## 04_Triage
Six findings, four routes
Counsel first; fix what fits the weeks and costs less than the buyer would take; disclose above the line; leave below it.
Weeks left before the room opens |  | 7
Materiality line, ₹ lakh of expected exposure |  | 2
Buyer's caution on what it finds itself |  | 1.5
Related-party and SHA questions to counsel |  | Yes
Issue | Finding | At stake | Probability | Expected | Cost to fix | Weeks to fix | Already cured | Curable in time | Governance | Route
I-03 | Small enterprise dues paid late | 0.0041735 | 1 | 0.0041735 | 0 | 0 | Yes | Yes | No | Leave
I-04 | Hoskote lease with a founder’s mother | 0.132 | 0.5 | 0.066 | 0.02 | 5 | No | Yes | Yes | Counsel
I-07 | FY25 PF on basic pay only | 0.032832 | 0.9 | 0.029549 | 0.032832 | 4 | No | Yes | No | Fix
I-08 | Gratuity without an actuarial valuation | 0.07 | 1 | 0.07 | 0.005 | 3 | No | Yes | No | Fix
I-10 | ESOP letters before the resolution | 0 | 1 | 0 | 0 | 4 | No | Yes | No | Fix
I-11 | PAS-3 filed late | 0.022 | 1 | 0.022 | 0 | 16 | No | No | No | Disclose
Findings fixed |  | 3
Findings disclosed |  | 1
Findings left |  | 1
Findings to counsel |  | 1
Expected exposure disclosed |  | 0.022
Cost of the fixes |  | 0.037832
Exposure workings
PAS-3 due date |  | 2025-05-15
PAS-3 filed |  | 2025-07-09
Days late |  | 55
Penalty a day, ₹ |  | 1000
Cap for each person, ₹ |  | 2500000
Persons liable: the company and three directors |  | 4
PAS-3 penalty |  | 0.022
FY25 support staff paid PF on basic |  | 12
Basic a month, ₹ |  | 9000
Wages with the universal allowance, ₹ |  | 18000
PF wage ceiling in FY25, ₹ |  | 15000
PF, EDLI and administration rate |  | 25%
Months |  | 12
FY25 PF shortfall |  | 0.0216
Average months of delay to payment |  | 26
Section 7Q interest rate a year |  | 12%
Section 14B damages rate a month |  | 1%
Interest |  | 0.005616
Damages |  | 0.005616
FY25 PF with interest and damages |  | 0.032832
Hoskote rent a year |  | 0.24
Market rent a year |  | 0.192
Months from April 2024 to December 2026 |  | 33
Rent paid above market |  | 0.132
Small enterprise dues beyond 45 days at 31 March 2026 |  | 0.2
Days overdue when paid |  | 46
Bank rate |  | 5.5%
Section 16 interest paid |  | 0.0041735
Gratuity shortfall against an actuarial valuation, estimate |  | 0.07

## 05_Remediation
The remediation plan
Ten actions, each with one owner, what it waits for, its duration and the document that closes it.
ID | Action | Owner | Weeks | Waits for | Evidence of closure
A | Actuarial valuation of gratuity | Finance lead | 3 | Nothing | Actuary’s report
B | FY25 PF shortfall computed by employee and month | HR and payroll | 1 | Nothing | Working by employee
C | Revised PF returns filed and paid with interest | HR and payroll | 2 | B | Return numbers and challans
D | Market rent study for the Hoskote warehouse | Founders’ office | 2 | Nothing | Valuer’s letter
E | Board meeting: lease on market terms, ESOP regrant, PAS-3 position | Company secretary | 1 | D | Signed minutes
F | Investor consent under the SHA | Founders’ office | 2 | E | Consent letter
G | ESOP regrant letters issued | HR and payroll | 1 | E, F | Resolution and grant letters
H | Counsel’s note on the PAS-3 penalty | Company secretary | 2 | Nothing | Counsel’s note
I | Adjudication application filed with the Registrar | Company secretary | 1 | H | Filing acknowledgement
J | Board takes the readiness report and the gratuity true-up | Finance lead | 1 | A, C, G, I | Signed minutes

## 06_Critical_Path
The critical path against 4 January 2027
Each action starts when everything it waits for has finished. Weeks count from the plan's start.
Sweep closes |  | 2026-11-13
Term sheet and data room |  | 2027-01-04
Investor consent sought alongside the board meeting |  | No
Weeks after the sweep before the plan starts |  | 0
ID | Action | Weeks | Starts | Finishes
A | Actuarial valuation of gratuity | 3 | 0 | 3
B | FY25 PF shortfall computed by employee and month | 1 | 0 | 1
C | Revised PF returns filed and paid with interest | 2 | 1 | 3
D | Market rent study for the Hoskote warehouse | 2 | 0 | 2
E | Board meeting: lease on market terms, ESOP regrant, PAS-3 position | 1 | 2 | 3
F | Investor consent under the SHA | 2 | 3 | 5
G | ESOP regrant letters issued | 1 | 5 | 6
H | Counsel’s note on the PAS-3 penalty | 2 | 0 | 2
I | Adjudication application filed with the Registrar | 1 | 2 | 3
J | Board takes the readiness report and the gratuity true-up | 1 | 6 | 7
Plan weeks |  | 7
Finish date |  | 2027-01-01
Days to spare before 4 January |  | 3
Formulas:
Weeks = C4+7*C7+7*[Weeks, row above]

## 07_Report
The one-page report on 4 January 2027
What the plan closed, the score on the same weights, and the three findings the founder hears first.
FY25 PF paid with interest |  | Yes
Gratuity valued by an actuary |  | Yes
ESOP regranted after consent |  | Yes
Lease approved on market terms with consent |  | Yes
Evidence requests for the unknowns returned |  | Yes
Buyer's caution on what it finds itself |  | 1.5
Issue | Finding | Expected | Price effect if found | After the plan
I-03 | Small enterprise dues paid late | 0.0041735 | 0.0062603 | 0
I-04 | Hoskote lease above market | 0.066 | 0.099 | 0.066
I-07 | FY25 PF on basic pay only | 0.029549 | 0.044323 | 0.005616
I-08 | Gratuity without an actuarial valuation | 0.07 | 0.105 | 0.07
I-10 | ESOP letters before the resolution | 0 | 0 | 0
I-11 | PAS-3 filed late | 0.022 | 0.033 | 0.022
Price effect before the plan |  |  | 0.28758
Price effect after the plan |  |  |  | 0.16362
Price the plan protects |  |  |  | 0.12397
Rank | Finding the founder hears first | Price effect
1 | Gratuity without an actuarial valuation | 0.07
2 | Hoskote lease above market | 0.066
3 | PAS-3 filed late | 0.022
Readiness score at the sweep |  | 79.13%
Readiness score on 4 January |  | 96.06%
ID | Weight | At the sweep | On 4 January | Credit
R-01 | 3 | clean | clean | 1
R-02 | 3 | clean | clean | 1
R-03 | 3 | clean | clean | 1
R-04 | 3 | gap | gap | 0
R-05 | 3 | gap | clean | 1
R-06 | 2 | clean | clean | 1
R-07 | 2 | clean | clean | 1
R-08 | 3 | gap | clean | 1
R-09 | 2 | clean | clean | 1
R-10 | 2 | clean | clean | 1
R-11 | 1 | clean | clean | 1
R-12 | 2 | unknown | clean | 1
R-13 | 3 | clean | clean | 1
R-14 | 2 | clean | clean | 1
R-15 | 2 | clean | clean | 1
R-16 | 2 | clean | clean | 1
R-17 | 3 | clean | clean | 1
R-18 | 2 | clean | clean | 1
R-19 | 2 | gap | clean | 1
R-20 | 2 | unknown | clean | 1
R-21 | 2 | clean | clean | 1
R-22 | 2 | clean | clean | 1
R-23 | 2 | clean | clean | 1
R-24 | 3 | clean | clean | 1
R-25 | 2 | clean | clean | 1
R-26 | 2 | clean | clean | 1
R-27 | 2 | unknown | clean | 1
R-28 | 2 | unknown | unknown | 0.5
R-29 | 1 | unknown | clean | 1
R-30 | 3 | clean | clean | 1
R-31 | 1 | clean | clean | 1
R-32 | 3 | clean | clean | 1
R-33 | 2 | unknown | clean | 1
R-34 | 3 | clean | clean | 1
R-35 | 2 | unknown | unknown | 0.5
R-36 | 3 | gap | clean | 1
R-37 | 3 | clean | clean | 1
R-38 | 1 | clean | clean | 1
R-39 | 2 | unknown | clean | 1
R-40 | 1 | clean | clean | 1
R-41 | 3 | clean | clean | 1
R-42 | 3 | gap | clean | 1
R-43 | 2 | clean | clean | 1
R-44 | 1 | clean | clean | 1
R-45 | 1 | clean | clean | 1
R-46 | 2 | unknown | clean | 1
R-47 | 2 | clean | clean | 1
R-48 | 1 | clean | clean | 1
R-49 | 2 | clean | clean | 1
R-50 | 3 | clean | clean | 1
R-51 | 3 | clean | clean | 1
R-52 | 2 | clean | clean | 1
R-53 | 1 | clean | clean | 1
R-54 | 2 | unknown | clean | 1
R-55 | 2 | clean | clean | 1
R-56 | 3 | clean | clean | 1
R-57 | 2 | clean | clean | 1
R-58 | 1 | clean | clean | 1
R-59 | 1 | clean | clean | 1
R-60 | 1 | clean | clean | 1

## 08_AI_Spec
Specification for an AI tool
Attach this workbook and give the tool the text below. Score its answer against 09_Answer_Check.
1 | Company: Kalasu Home Appliances Private Limited, an unlisted Indian private company under Accounting Standards. Series B term sheet and data room on 4 January 2027; the sweep closed on 13 November 2026.
2 | Score 01_Checklist by severity: weight high 3, medium 2, low 1; credit clean 1, unknown 0.5 (or 0 if unknowns are gaps), gap 0. Never score an unknown as clean.
3 | Load 02_Request_Load: open requests are requests less what the data room already holds; hours are open requests times hours each; weeks are an owner's hours over the hours a week they can give; the first pass ends when the slowest owner ends.
4 | Route each finding in 04_Triage: counsel first for related-party and SHA questions; fix when the cure fits the weeks left and costs no more than the expected exposure times the caution factor; disclose when the expected exposure is at or above the line; otherwise leave. A cured default is still disclosed.
5 | Build 06_Critical_Path: each action starts when everything it waits for has finished. Report the finish date and the days to spare before 4 January 2027.
6 | Report 07_Report: lead with the three findings with the largest price effect after the plan, then the score at the sweep and on 4 January on the same weights, then what is fixed, disclosed and still unknown.
7 | Cite the Companies Act, 2013 sections 42(8), 42(9), 188(3), 403 and 454; the EPF Act, 1952 sections 7Q and 14B and the Code on Social Security, 2020 from 21 November 2025; Section 43B(h) of the 1961 Act and Section 37(2)(g) with 37(3) of the 2025 Act.

## 09_Answer_Check
Answer check
Course figures against this workbook's formulas. A status of Agrees means the difference is within the tolerance.
Figure | Course figure | This workbook | Difference | Status | Tolerance
Requests on the list | 180 | 180 | 0 | Agrees | 0
Open after the data room | 98 | 98 | 0 | Agrees | 0
Weeks to a complete first pass | 10 | 10 | 0 | Agrees | 0.005
Readiness score at the sweep | 79.13% | 79.13% | -4.173e-05% | Agrees | 0.05%
Readiness score, unknowns as gaps | 71.65% | 71.65% | 4.331e-05% | Agrees | 0.05%
Gaps | 6 | 6 | 0 | Agrees | 0
Unknown items | 10 | 10 | 0 | Agrees | 0
Findings fixed | 3 | 3 | 0 | Agrees | 0
Findings disclosed | 1 | 1 | 0 | Agrees | 0
Findings left | 1 | 1 | 0 | Agrees | 0
Findings to counsel | 1 | 1 | 0 | Agrees | 0
Expected exposure disclosed | 0.022 | 0.022 | 0 | Agrees | 5e-05
Plan weeks | 7 | 7 | 0 | Agrees | 0
Days to spare before 4 January | 3 | 3 | 0 | Agrees | 0
Readiness score on 4 January | 96.06% | 96.06% | -7.874e-06% | Agrees | 0.05%
Price effect before the plan | 0.28758 | 0.28758 | 4.8041e-07 | Agrees | 5e-05
Price effect after the plan | 0.16362 | 0.16362 | -2.7756e-17 | Agrees | 5e-05
Price the plan protects | 0.12397 | 0.12397 | 4.8041e-07 | Agrees | 5e-05
PAS-3 penalty | 0.022 | 0.022 | 0 | Agrees | 5e-05
FY25 PF shortfall | 0.0216 | 0.0216 | 0 | Agrees | 5e-05
FY25 PF with interest and damages | 0.032832 | 0.032832 | 0 | Agrees | 5e-05